## Contacts
Mutual Evaluation Plan
Nextgen Clearing | Strategy
Filipe Santos | Henry Allum
Product Team Leader | Account Director
Primary Contact | Primary Contact
Ruben Iversen | Ludivine Fevre
CTO | Sales Engineer
Technical Contact | Technical Contact
Jean Doblustaine | Jamie Longmuir
Deptuty CEO | NEU Sales Director
Executive Sponsor | Executive Sponsor

## Project Plan Timeline
Project Plan Timeline
Please indicate the date and status of different milestones:
Milestone | Description | Start Date | Completion Date | Owner Strategy | Owner Nextgen | Status
Scoping Call | Identify and align on Business Objectives, Use Cases, Implementation Requirements, Success Criteria, Key Milestones and Stakeholders |  |  |  |  | Complete
Success Criteria Alignment | Agreement on what we want to validate as part of the PoV | 20/5/26 | 27/5/26 |  |  | Scheduled
Data set validation | Is the data that we are preparing have the right data to answer the agreed usecases |  |  |  |  | Not Yet Scheduled
Licencing Requirments | Scope the user volumn required to ensure commerically the PoV makes sense |  |  |  |  | Not Yet Scheduled
Executive Alignment | Connect Executive Sponsors to ensure alignment on PoV objectives and outcomes |  |  |  |  | Not Yet Scheduled
Kick-off call | Kick- off PoV |  |  |  |  | Not Yet Scheduled
Workshop 1 | Strategy to demonstrate Strategy functinality inline with PoV SC |  |  |  |  | Not Yet Scheduled
Nextgen user testing | Nextgen users to test functionality and confirm Strategy aligns to Nextgen SC |  |  |  |  | Not Yet Scheduled
Workshop 2 | Finalised validation against agreed SC |  |  |  |  | Not Yet Scheduled
Success Criteria Validation | Session to discuss outstanding questions and sign-off on Success Criteria, and if successful, move into Pricing & Packaging |  |  |  |  | Not Yet Scheduled
Info Sec & Security Review | Align and ensure Strategy's Tech & Security Policies are approved by Nextgen Clearing |  |  |  |  | Not Yet Scheduled
Onboarding Scope Validation | Review onboarding scope and incorporate any learnings from the proof-of-value |  |  |  |  | Not Yet Scheduled
Pricing & Packaging | Begin reviewing commercial terms in more detail to work towards mutual agreement |  |  |  |  | Not Yet Scheduled
Legal Review | Connect legal teams to discuss T&Cs |  |  |  |  | Not Yet Scheduled
Execute Contract | Agreement signed by both executive teams |  |  |  |  | Not Yet Scheduled
Target Onboarding Date | Partnership kickoff with your Account Manager (assuming Strategy met Success Criteria, agreement execution should occur at least one week prior to this date) |  |  |  |  | Not Yet Scheduled
Target Go Live Date | Date MSTR platform is live ahead of Dublin Event |  |  |  |  | Not Yet Scheduled

## Go Live Plan
Go Live Plan
Action | May | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September
| 25/5 | 2026-01-06 | 2026-08-06 | 15/6 | 22/6 | 29/6 | 2026-06-07 | 13/7 | 20/7 | 27/7 | 2026-03-08 | 2026-10-08 | 17/8 | 24/8 | 31/8 | 2026-03-09
Scoping Call
Success Criteria Alignment
Executive Alignment
Data set validation
Kick-off call
Workshop 1
Nextgen user testing
Workshop 2
Success Criteria Validation
Onboarding Scope Validation
Pricing & Packaging
Legal Review
Execute Contract
Target Onboarding Date
Target Go Live Date

## NextGen Success Criteria
Success Criteria
What are the use-cases you intend to use? What are your requirements for this solution? Please edit this!
Use Case | Requirements | Priority | included in POV | Note | Validated | Date
Use Case 1: Intergration with Customer Ecosystem | Compatibilty with current and future Data sources and systems |  | No | POV will be based on Excel files
| Front-end tools: Compatibility with Excel, Power Point, Qlik… |  | Yes | Tools to be tested in POV: Strategy reports, dashboards, …
Share data through MCP, using our own AI to help with data modelling
| Ability to create reports through drag and drop, add totals, drill down into other dimensions… |  | Yes
| Ability to created dynamic dashboards with multiple chapters and pages |  | Yes
| Accelerate and facilitate dashboards creation through reusability: ability to leveragge reusable templates, color palette, theme |  | Yes
| Dashboard - Ability to export dashboards and visualizations |  | Yes
| Ability to create email subscriptions |  | Yes
| Enable users or administrators to receive alerts by email when a KPI metric value is reached |  | Yes
| Large library of visualizations including geospatial capabilities |  | Yes
Ability to create what-if-analysis
| Ability to embed dashboards in a portal |  | No
| The tool is available in different languages. Data can be translated. |  | ?
Quality and Availability of documentation and support
| The solution is open and offers a strong Roadmap to meet coming requirements |  | No
| Ability to track usages of the different assets |  | No
| Authentication/ ie. SSO support (Okta and OIDC - Keycloak) |  | No
| Ability to automate administration tasks through Python code and Apis |  | No
Use Case 2: Data Modelling with Mosaic | Data Modeling: Ability to create, modify and manage models in a graphical interface. Ability to create advanced metrics, used advances functions, time transformations (Last year, Last Month…) |  | Yes
| Ability to create virtual logical tables in the tool |  | Yes
| Ability to create models on top of relational datasource and files |  | Yes
| Data Cleaning: Ability to apply data preparation functions |  | Yes
| Data Models creation experience: Ease of creation for data architects and business users. Time to create the model |  | Yes
| Performance: capacity to process complex query and large datasets. Ability to monitor and troubleshoot potential performance issues. |  | Yes
| Compare the cost of performing data operations (querying, reporting, cube publication…) compared to other solution |  | No | Relevant for Cloud data platform with compute costs based on usage
| Connectivity type: Ability to choose among Live query and in memory depending on use case, and mix both approaches if relevant |  | Yes | Pov
| Security: Ability to define Row-level security, column-level security and privileges at group/ user level. Ability to identify and monitor sensitive data. |  | Yes | POV
| Scalability: Ability to handle high concurrency and large data volumes |  | No
| Portability: Ability to change the data source, connect other tools |  | No
| CI/CD integration: Ability to export Mosaic models to a YAML file and restore models from a YAML file. Save and restore Mosaic models from Git. |  | No
Use Case 3: Data Exploration / Conversational Analytics | Agents creation: Ease of creation and customization of agents, creation time |  | Yes
| Agents answers are accurate and can be easily checked |  | Yes
| Agents answers are less than 20 seconds |  | Yes
| Ability to consume agents in Strategy Library, Teams, Mobile, LLM (which one?), ability to embed agents in third-party website |  | Yes
| Ability to to allow business users to ask questions in natural language on the dashboard data. |  | Yes
| Ability to use natural language or upload an image to create visuals in a dashboard — or even entire dashboard pages with several graphs. |  | Yes
| Ability to generate natural language descriptions of grids or graphs, tuned by a prompt defined by the dashboard creator. |  | Yes